## Velocity Tracker
Sprint | Planned Points | Completed Points | Team Comments
Sprint 1 | 20 | 18 | Storyboard took longer than expected
Sprint 2 | 25 | 23 | Good velocity, but some tasks carried over
Sprint 3 | 28 | 28 | Smooth sprint with well-balanced workload
Sprint 4 | 22 | 19 | Lost time due to weather uncertainties