## Sprint Backlog
Task ID | Task Description | Owner | Status | Priority | Story Points | Deadline | Notes
T001 | Storyboard development | Creative Lead | In Progress | High | 5 | 2025-06-20 | First draft reviewed
T002 | Location scouting | Producer | Not Started | Medium | 3 | 2025-06-22 | Scouting in Mumbai
T003 | Casting confirmation | Talent Manager | Completed | High | 2 | 2025-06-18 | All talent onboarded
T004 | Wardrobe finalization | Stylist | In Progress | High | 3 | 2025-06-24 | Waiting for client approval
T005 | Call sheet preparation | Coordinator | Not Started | Medium | 2 | 2025-06-25 | Dependent on cast schedule