## Slide 1: Ather Scooter TVC – Project Summary
An update on pre-production, timelines, and next steps.

## Slide 2: Project Status – June 21, 2025
- Script: Finalized and signed
- Locations: Booked
- Talent: Confirmed
- Shoot Dates: July 5–7
- Risk: Rain during outdoor shoot
- Mitigation: Backup indoor studio in planning

## Slide 3: Next Steps
- Complete prop sourcing
- Share call sheets with all departments
- Conduct pre-shoot briefing
- Confirm rain contingency with client